## Sprint Backlog #2
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
Sprint 4 | Complete Sprint 3!!!!!!
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
[5 empty] | Tuesday 4/19 | Thursday 4/21 | Tuesday 5/3 | Thursday 5/5 | Tuesday 5/3
User Story #1 | 8
Colin Conway |  | Route Distance Refactor | Completed | 2 | 2 | 0 | 0 | 0 | 0
Colin Conway |  | Compare Distance between route strategies | In Progress | 10 | 10 | 10 | 10 | 10 | 10
User Story #2 | 1
Thomas Abato |  | Observer GUI | In Progress | 10 | 10 | 10 | 10 | 10 | 10
User Story #3 | 5
Luke Suppa |  | UML Diagram | In Progress | 8 | 8 | 8 | 8 | 8 | 8
User Story #4 | 8
User Story #5 | 3
TOTAL |  |  |  | 30 | 30 | 28 | 28 | 28 | 28