## PRODUCT BACKLOG
Sandwich Truck Project
SANDWICH TRUCK PRODUCT BACKLOG
User Story ID | User Story | Estimate (size) | Priority | Sprint | Task owner | Estimated effort
US001 | Be able to model the truck neighborhood with destinations clearly marked on the map. | Medium | 5 | 1 | Product Owner | 48
US002 | Be able to display the truck neighborhood using a Graphical User Interface. | Large | 5 | 1 | Product Owner | 48
US003 | Create a file of 100 random addresses that are timestamped with the time the order is recieved | Small | 5 | 1 | Product Owner | 4
US004 | Create a Priority Queue of deliverly locations where the priority is the time the order was received. This Priority Queue will represent the order in which deliveries are made. | Small | 4 | 2 | Product Owner | 4
US005 | Be able to compute a delivery route for the truck based on time of order. | Medium | 4 | 2 | Product Owner | 36
US005 | Display the neighborhood showing the truck moving from destination to destination. | Large | 3 | 2 | Product Owner | 48
US006 | Add sandwich orders to the file containing destinations and time of order. | Medium | 2 | 3 | Product Owner | 6
US007 | Model the making of sandwich orders | Medium | 2 | 3 | Product Owner | 6
US008 | Model the delivery of an order. Truck should pause and a popup window will display the customer order being delivered. | Small | 2 | 4 | Product Owner | 4
US009 | Compute distance traveled to make all deliveries | Small | 4 | 3 | Product Owner | 4
US010 | Compare the distances traveled by the alternate routing strategies and display these distances to the monitor. | Medium | 1 | 3 | Product Owner | 24
US011 | Truck will return to it's Service Center when there are no more orders to deliver or when in need of gas or supplies. | Small | 1 | 4 | Product Owner | 4
US012 | Change the size of a block from 1 mile to 1/10 of a mile. This should provide more accurate travel distances by the truck. | Small | 1 | 4 | Product Owner | 6
US013 | An order entry user interface for taking a customer order. This can replace the randomly generated sandwich orders which is part of the current system. | Medium | 2 | 4 | Product Owner | 12
US014 | Create a route for the truck based on the address of the order. Want to minimized distance the truck travels. | Medium | 4 | 2 | Product Owner | 24
US015 | Create a route for the truck based on the address of the order. The truck is only allowed to make right-hand turns. | Medium | 4 | 2 | Product Owner | 20
US016 | Customers who have made orders should be able to keep track of the location of the Sandwich Truck. | Medium | 5 | 3 | Product Owner | 16
US017 | A listing of the customers currently waiting on delivery should be diplayable to the display showing the time of order, the address of the order, The items ordered, and the location of the Sandwich Truck. | Medium | 5 | 4 | Product Owner | 16
US018 | User should be able to pick which type of routing strategy is used for a simulation. | Small | 5 | 3 | Product Owner | 4
Note on D7: stakeholdermap.com: Whatever method you are using for estimation. It could be story points, Fibonacci scale or T-shirt sizes - small, medium, large.
Note on E7: stakeholdermap.com: To change the Priority menu click on the DROPDOWN MENUS worksheet.
Note on F7: stakeholdermap.com: To change the Priority menu click on the DROPDOWN MENUS worksheet.
Note on G7: stakeholdermap.com: An optional field for the person responsible for the completion of the User Story.
Note on H7: stakeholdermap.com: This is an optional field for estimated effort in hours or days.

## PROJECT DETAILS
PROJECT NUMBER
PROJECT NAME
PROJECT MANAGER
DATE
VERSION

## DROPDOWN MENUS
PRIORITY | SPRINT
1 | 1
2 | 2
3 | 3
4 | 4
5 | 5
6
7
8
9
10
TO EDIT THE DROPDOWN MENUS
Click on the Data tab. Under Data Tools, select Data Validation. Under Settings change the Source to match the values you want to appear in the menu.
TO DELETE THE DROPDOWN MENUS
Click on the Data tab. Under Data Tools, select Data Validation. Under Settings change the Allow to Any value.

## RESOURCES
Useful resources
Burndown Chart Template
Daily Scrum Meeting Template
Project Management Templates
The Top 50 Business Risks (and how to manage them)!
Issue Log Template [free download]
End Project Report Template
Risk Register Template
Stakeholder Management Templates
Work Breakdown Structure (WBS) template in Excel