## Sprint Backlog #2
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
Sprint 1 Goal | Model the neighborhood and GUI foundations. Create a batchfile of 100 randomly generated orders
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | SPRINT REVIEW
[5 empty] | Tuesday 3/8 | Thursday 3/10 | Tuesday 3/15 | Thursday 3/17 | Tuesday 3/22 | Thursday 3/24 | Thursday 3/24
User Story #1 | 8
Task Add Timestamps |  | Colin Conway |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Task Priority Queu |  | Colin Conway |  | 6 | 6 | 5 | 5 | 4
Task UML diagram |  | Colin Conway |  | 6 | 6 | 6 | 6 | 6
Task
User Story #2 | 1
Task Display Truck |  | Thomas Abatop |  | 10 | 10 | 4 | 4
Task
Task
Task
User Story #3 | 5
Task Delivery Route |  | Luke Suppa |  | 8 | 8 | 8 | 8
Task
Task
Task
User Story #4 | 8
Task Delivery route based on time |  | Jake Clause |  | 8 | 8
Task
Task
Task
User Story #5 | 3
Task
Task
Task
Task
TOTAL |  |  |  | 40 | 40 | 23 | 23 | 10 | 0 | 0 | 0

## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
Sprint 1 Goal | Model the neighborhood and GUI foundations. Create a batchfile of 100 randomly generated orders
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | SPRINT REVIEW
[5 empty] | Tursday | Thursday | Tuesday | Thursday | Tuesday | Thursday
User Story #1 | 8
Task |  |  |  | 7 | 5 | 3 | 0 | 0 | 10 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 5 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 6 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 4 | 0 | 0
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 |  | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 |  | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 |  | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 |  | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 |  | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 |  | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 |  | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 |  | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 |  | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 |  | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 |  | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 |  | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 |  | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 |  | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 |  | 0 | 1
TOTAL |  |  |  | 78 | 60 | 59 | 41 | 20 | 25 | 18 | 14

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
Sprint 1 Goals | Model the neighborhood and GUI foundatations. Create a batch file with 100 orders.
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 (Model Neighborhood)
Task: Map |  | Colin Conway |  | 26 | 26 | 20 | 14 | 8 | 0
Task:
Task Map |  | Luke Suppa |  | 18 | 18 | 15 | 10 | 6 | 0
Task
User Story #2 (GUI display of truck)
Task: GUI |  | Thomas Abato |  | 28 | 26 | 24 | 16 | 8 | 0
Task; JavaDocs
Task
Task
User Story #3 (100 orders)
Task: create batch file |  | Jake Clause |  | 8 | 6 | 5 | 2 | 1 | 0
Task Random Houses |  | Jake Clause |  | 10 | 8 | 6 | 5 | 3 | 0
Task
Task
User Story #4 (other)
Task: UML diagram |  | Luke Suppa |  | 2 | 2 | 2 | 1 | 1 | 0
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 92 | 86 | 72 | 48 | 27 | 0 | 0